## More -->
Free Tutorials
Browse through my free Excel tutorials to discover dashboard tips, chart tricks and advanced formula techniques.
Courses to help you succeed
If you'd like to learn Excel in a structured way and in your own time, check out my bestselling courses:
Favorite Resources
Check out my list of favorite resources. It includes links to Excel books I've found helpful, courses on topics I'm interested in such as Power Query, data science and more.
Sharing & Learning
Feel free to share this with anyone who can benefit!
Learn More
Free Tutorials
Start Learning
Browse
After having taken other VBA courses, I can say with certainty that this is the best by far, it is amazing the amount of tips, tricks and shortcuts that Leila teaches us and others do not. It shows the effort and love that Leila delivers in each course she does.
Felix Valecillos (Excel VBA course)
This is a great course that taught me new things and also demonstrated new ways to apply existing techniques in ways I had not previously considered or knew where possible. I really enjoyed and benefited from the teaching style. Leila chunks the more complicated subject matter to make it easier to grasp. As a result my Excel capability just increased significantly and I have no hesitation recommending this course.
Ade Vaughan (Excel Dashboard course)

## Quick_Gantt
Quick Gantt Chart
Task | Start date | # Working days | End date | # days | task # | Holidays
Design completed | 2017-01-02 | 15 | 2017-01-24 | 22 | 1 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 19 | 2 | 2017-01-06
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 16 | 3 | 2017-04-16
Initial build | 2017-02-17 | 13 | 2017-03-08 | 19 | 4 | 2017-04-17
Data migration | 2017-03-08 | 7 | 2017-03-17 | 9 | 5 | 2017-05-01
User training | 2017-03-17 | 13 | 2017-04-05 | 19 | 6 | 2017-05-25
Testing | 2017-04-05 | 10 | 2017-04-20 | 15 | 7 | 2017-06-04
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 13 | 8 | 2017-06-05
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 21 | 9 | 2017-06-15
2017-08-15
2017-10-26
2017-11-01
2017-12-08
2017-12-25
2017-12-26
# Working days
Design completed | 15
Admin training | 13
Address IT issues | 12
Initial build | 13
Data migration | 7
User training | 13
Testing | 10
Parallel run | 8
Sign-off | 15
Formulas:
End date = IF([Start date]="","",WORKDAY([Start date],C4,G4:G18))

## Full_Gantt
Fully Featured Gantt Chart
Data preparation
| Plan |  |  | Actual |  |  |  |  | Project Timeline: Plan View
Task | Start date | # Working days | End date | Start date | # Working days | End date | % Completion | Task | Start date | # days | # days completed | Holidays
Design completed | 2017-01-02 | 15 | 2017-01-24 | 2017-01-02 | 5 | 2017-01-10 | 100% | Design completed - 15 WD | 2017-01-02 | 22 | 0 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 2017-01-10 | 10 | 2017-01-24 | 80% | Admin training - 13 WD | 2017-01-13 | 19 | 0 | 2017-01-06
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 2017-02-01 | 12 | 2017-02-17 | 50% | Address IT issues - 12 WD | 2017-02-01 | 16 | 0 | 2017-04-16
Initial build | 2017-02-17 | 13 | 2017-03-08 | 2017-02-17 | 13 | 2017-03-08 | 20% | Initial build - 13 WD | 2017-02-17 | 19 | 0 | 2017-04-17
Data migration | 2017-03-08 | 7 | 2017-03-17 | 2017-03-08 | 7 | 2017-03-17 |  | Data migration - 7 WD | 2017-03-08 | 9 | 0 | 2017-05-01
User training | 2017-03-17 | 13 | 2017-04-05 | 2017-03-17 | 13 | 2017-04-05 |  | User training - 13 WD | 2017-03-17 | 19 | 0 | 2017-05-25
Testing | 2017-04-05 | 10 | 2017-04-20 | 2017-04-05 | 10 | 2017-04-20 |  | Testing - 10 WD | 2017-04-05 | 15 | 0 | 2017-06-04
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 2017-04-20 | 8 | 2017-05-03 |  | Parallel run - 8 WD | 2017-04-20 | 13 | 0 | 2017-06-05
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 2017-05-03 | 15 | 2017-05-24 |  | Sign-off - 15 WD | 2017-05-03 | 21 | 0 | 2017-06-15
2017-08-15
2017-10-26
2017-11-01
Select Scenario: | Plan | [10 empty] | 2017-12-08
2017-12-25
2017-12-26

## Full_Gantt_Plan_Actual_one_view
Fully Featured Gantt Chart: ONE VIEW
Data preparation
| Plan |  |  | Actual
Task | Start date | # Working days | End date | Start date | # Working days | End date | % Completion | Task | Start actual date | # days | # days completed | Start Plan date | # days | Y- axis for Plan | Current day | Holidays
Design completed | 2019-01-02 | 15 | 2019-01-23 | 2019-01-02 | 5 | 2019-01-09 | 100% | Design completed | 2019-01-02 | 7 | 7 | 2019-01-02 | 21 | 8.2 | 2019-04-04 | 2019-01-01
Admin training | 2019-01-13 | 13 | 2019-01-30 | 2019-01-10 | 10 | 2019-01-24 | 80% | Admin training | 2019-01-10 | 14 | 11.2 | 2019-01-13 | 17 | 7.2 | 2019-04-04 | 2019-04-22
Address IT issues | 2019-02-01 | 12 | 2019-02-19 | 2019-02-01 | 12 | 2019-02-19 | 50% | Address IT issues | 2019-02-01 | 18 | 9 | 2019-02-01 | 18 | 6.2 | 2019-04-04 | 2019-05-01
Initial build | 2019-02-17 | 13 | 2019-03-06 | 2019-02-17 | 13 | 2019-03-06 | 20% | Initial build | 2019-02-17 | 17 | 3.4 | 2019-02-17 | 17 | 5.2 | 2019-04-04 | 2019-05-30
Data migration | 2019-03-08 | 7 | 2019-03-19 | 2019-03-08 | 7 | 2019-03-19 |  | Data migration | 2019-03-08 | 11 | 0 | 2019-03-08 | 11 | 4.2 | 2019-04-04 | 2019-06-10
User training | 2019-03-17 | 13 | 2019-04-03 | 2019-03-17 | 13 | 2019-04-03 |  | User training | 2019-03-17 | 17 | 0 | 2019-03-17 | 17 | 3.2 | 2019-04-04 | 2019-06-20
Testing | 2019-04-05 | 10 | 2019-04-19 | 2019-04-05 | 10 | 2019-04-19 |  | Testing | 2019-04-05 | 14 | 0 | 2019-04-05 | 14 | 2.2 | 2019-04-04 | 2019-08-15
Parallel run | 2019-04-20 | 8 | 2019-05-03 | 2019-04-20 | 8 | 2019-05-03 |  | Parallel run | 2019-04-20 | 13 | 0 | 2019-04-20 | 13 | 1.2 | 2019-04-04 | 2019-11-01
Sign-off | 2019-05-03 | 15 | 2019-05-24 | 2019-05-03 | 15 | 2019-05-24 |  | Sign-off | 2019-05-03 | 21 | 0 | 2019-05-03 | 21 | 0.2 | 2019-04-04 | 2019-12-24
2019-12-25
2019-12-26

## Gantt_with_Dependency
Gantt Chart with Dependency
Data preparation
|  | Plan |  |  | Actual
Task | Dependency | Start date | # Working days | End date | Start date | # Working days | End date | % Completion | Task | Start actual date | # days | # days completed | Start Plan date | # days | Y- axis for Plan | Current day | Y-axis for Dependency | Dependency End Date | Relative Dependency Y position | Days between Start and Dependency End |  | Holidays
Design completed | Design completed | 2019-01-02 | 15 | 2019-01-23 | 2019-01-02 | 5 | 2019-01-09 | 100% | Design completed | 2019-01-02 | 7 | 7 | 2019-01-02 | 21 | 8.2 | 2019-04-04 | 8.3 | 2019-01-09 | 0 | -7 |  | 2019-01-01
Admin training | Design completed | 2019-01-13 | 13 | 2019-01-30 | 2019-01-10 | 10 | 2019-01-24 | 80% | Admin training | 2019-01-10 | 14 | 11.2 | 2019-01-13 | 17 | 7.2 | 2019-04-04 | 7.3 | 2019-01-09 | -1 | 1 |  | 2019-04-22
Address IT issues | Admin training | 2019-02-01 | 12 | 2019-02-19 | 2019-02-01 | 12 | 2019-02-19 | 50% | Address IT issues | 2019-02-01 | 18 | 9 | 2019-02-01 | 18 | 6.2 | 2019-04-04 | 6.3 | 2019-01-24 | -1 | 8 |  | 2019-05-01
Initial build | Initial build | 2019-02-17 | 13 | 2019-03-06 | 2019-02-17 | 13 | 2019-03-06 | 20% | Initial build | 2019-02-17 | 17 | 3.4 | 2019-02-17 | 17 | 5.2 | 2019-04-04 | 5.3 | 2019-03-06 | 0 | -17 |  | 2019-05-30
Data migration | Admin training | 2019-03-08 | 7 | 2019-03-19 | 2019-03-08 | 7 | 2019-03-19 |  | Data migration | 2019-03-08 | 11 | 0 | 2019-03-08 | 11 | 4.2 | 2019-04-04 | 4.3 | 2019-01-24 | -3 | 43 |  | 2019-06-10
User training | Admin training | 2019-03-17 | 13 | 2019-04-03 | 2019-03-17 | 13 | 2019-04-03 |  | User training | 2019-03-17 | 17 | 0 | 2019-03-17 | 17 | 3.2 | 2019-04-04 | 3.3 | 2019-01-24 | -4 | 52 |  | 2019-06-20
Testing | User training | 2019-04-05 | 10 | 2019-04-19 | 2019-04-05 | 10 | 2019-04-19 |  | Testing | 2019-04-05 | 14 | 0 | 2019-04-05 | 14 | 2.2 | 2019-04-04 | 2.3 | 2019-04-03 | -1 | 2 |  | 2019-08-15
Parallel run | Testing | 2019-04-20 | 8 | 2019-05-01 | 2019-04-20 | 8 | 2019-05-01 |  | Parallel run | 2019-04-20 | 11 | 0 | 2019-04-20 | 11 | 1.2 | 2019-04-04 | 1.3 | 2019-04-19 | -1 | 1 |  | 2019-11-01
Sign-off | Parallel run | 2019-05-03 | 15 | 2019-05-24 | 2019-05-03 | 15 | 2019-05-24 |  | Sign-off | 2019-05-03 | 21 | 0 | 2019-05-03 | 21 | 0.2 | 2019-04-04 | 0.3 | 2019-05-01 | -1 | 2 |  | 2019-12-24
2019-12-25
2019-12-26
Dependencies in grey in data prep. table and blue lines in Gantt Chart were added by Rico (one of our community members). Thank you Rico for taking the Gantt chart to another level!