## Notes
Overview
If you're interested to become better in Excel, check out my ONLINE COURSES.
Sharing & Learning
Feel free to share this with anyone who can benefit!
Visit my other free Excel Tutorials.
Notes

## Quick_Gantt
Quick Gantt Chart
Task | Start date | # Working days | End date | # days | task # | Holidays
Design completed | 2017-01-02 | 15 | 2017-01-24 | 22 | 1 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 19 | 2 | 2017-01-06
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 16 | 3 | 2017-04-16
Initial build | 2017-02-17 | 13 | 2017-03-08 | 19 | 4 | 2017-04-17
Data migration | 2017-03-08 | 7 | 2017-03-17 | 9 | 5 | 2017-05-01
User training | 2017-03-17 | 13 | 2017-04-05 | 19 | 6 | 2017-05-25
Testing | 2017-04-05 | 10 | 2017-04-20 | 15 | 7 | 2017-06-04
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 13 | 8 | 2017-06-05
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 21 | 9 | 2017-06-15
2017-08-15
2017-10-26
2017-11-01
2017-12-08
2017-12-25
2017-12-26
# Working days
Design completed | 15
Admin training | 13
Address IT issues | 12
Initial build | 13
Data migration | 7
User training | 13
Testing | 10
Parallel run | 8
Sign-off | 15
Formulas:
End date = IF([Start date]="","",WORKDAY([Start date],C4,G4:G18))

## Full_Gantt_Complete
Fully Featured Gantt Chart
Data preparation
| Plan |  |  | Actual |  |  |  |  | Project Timeline: Actual View
Task | Start date | # Working days | End date | Start date | # Working days | End date | % Completion | Task | Start date | # days | # days completed | Holidays
Design completed | 2017-01-02 | 15 | 2017-01-24 | 2017-01-02 | 5 | 2017-01-10 | 100% | Design completed - 5 WD | 2017-01-02 | 8 | 8 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 2017-01-10 | 10 | 2017-01-24 | 80% | Admin training - 10 WD | 2017-01-10 | 14 | 11.2 | 2017-01-06
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 2017-02-01 | 12 | 2017-02-17 | 50% | Address IT issues - 12 WD | 2017-02-01 | 16 | 8 | 2017-04-16
Initial build | 2017-02-17 | 13 | 2017-03-08 | 2017-02-17 | 13 | 2017-03-08 | 20% | Initial build - 13 WD | 2017-02-17 | 19 | 3.8 | 2017-04-17
Data migration | 2017-03-08 | 7 | 2017-03-17 | 2017-03-08 | 7 | 2017-03-17 |  | Data migration - 7 WD | 2017-03-08 | 9 | 0 | 2017-05-01
User training | 2017-03-17 | 13 | 2017-04-05 | 2017-03-17 | 13 | 2017-04-05 |  | User training - 13 WD | 2017-03-17 | 19 | 0 | 2017-05-25
Testing | 2017-04-05 | 10 | 2017-04-20 | 2017-04-05 | 10 | 2017-04-20 |  | Testing - 10 WD | 2017-04-05 | 15 | 0 | 2017-06-04
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 2017-04-20 | 8 | 2017-05-03 |  | Parallel run - 8 WD | 2017-04-20 | 13 | 0 | 2017-06-05
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 2017-05-03 | 15 | 2017-05-24 |  | Sign-off - 15 WD | 2017-05-03 | 21 | 0 | 2017-06-15
2017-08-15
2017-10-26
2017-11-01
Select Scenario: | Actual | [10 empty] | 2017-12-08
2017-12-25
2017-12-26