## Notes
Overview
If you're interested to become better in Excel, check out my ONLINE COURSES.
Sharing & Learning
Feel free to share this with anyone who can benefit!
Visit my other free Excel Tutorials.
Notes

## Workday
Task | Start date | # Working days | End date | Holidays
Design completed | 2017-01-02 | 8 | 2017-01-13 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 2017-01-06
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 2017-04-16
Initial build completed | 2017-02-17 | 13 | 2017-03-08 | 2017-04-17
Data migration | 2017-03-08 | 7 | 2017-03-17 | 2017-05-01
User training | 2017-03-17 | 13 | 2017-04-05 | 2017-05-25
Testing | 2017-04-05 | 10 | 2017-04-20 | 2017-06-04
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 2017-06-05
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 2017-06-15
2017-08-15
2017-10-26
2017-11-01
2017-12-08
2017-12-25
2017-12-26
Deadlines
Task Due | Due on Working day | 2017-05-01 | 2017-06-01
Estimate Data | 3 | 2017-05-04 | 2017-06-06
Main Financials | 4 | 2017-05-05 | 2017-06-07
Additional Reporting | 7 | 2017-05-10 | 2017-06-12
Formulas:
End date = IF([Start date]="","",WORKDAY([Start date],C3,G3:G17))
End date = WORKDAY(D22-1,[Start date],G3:G17)
Start date = [End date, row above]

## Networkday
|  | UK |  | Holidays
Task | Start date | # Working days | End date | Austria | UK
Design completed | 2017-01-02 | 8 | 2017-01-13 | 2017-01-01 | 2017-01-01
Admin training | 2017-01-13 | 13 | 2017-02-01 | 2017-01-06 | 2017-01-02
Address IT issues | 2017-02-01 | 12 | 2017-02-17 | 2017-04-16 | 2017-01-03
Initial build completed | 2017-02-17 | 13 | 2017-03-08 | 2017-04-17 | 2017-03-17
Data migration | 2017-03-08 | 6 | 2017-03-17 | 2017-05-01 | 2017-04-14
User training | 2017-03-17 | 13 | 2017-04-05 | 2017-05-25 | 2017-04-17
Testing | 2017-04-05 | 9 | 2017-04-20 | 2017-06-04 | 2017-05-01
Parallel run | 2017-04-20 | 8 | 2017-05-03 | 2017-06-05 | 2017-05-29
Sign-off | 2017-05-03 | 15 | 2017-05-24 | 2017-06-15 | 2017-07-12
|  |  |  | 2017-08-15 | 2017-08-07
|  |  |  | 2017-10-26 | 2017-08-28
|  |  |  | 2017-11-01 | 2017-11-30
|  |  |  | 2017-12-08 | 2017-12-25
|  |  |  | 2017-12-25 | 2017-12-26
2017-12-26
Deadlines
Task Due | Due on Working day | 2017-05-01 | 2017-06-01
Estimate Data | 3 | 2017-05-04 | 2017-06-06
Main Financials | 4 | 2017-05-05 | 2017-06-07
Additional Reporting | 7 | 2017-05-10 | 2017-06-12